Project Plan

chaos: Network Latency & Packet-Loss Chaos Emulator

| Field | Detail |
| --- | --- |
| Project | chaos: Network Latency & Packet-Loss Chaos Emulator |
| Student name | [YOUR NAME] |
| Roll no. / ID | [YOUR ROLL NO] |
| Course | [COURSE NAME / CODE] |
| Instructor | [INSTRUCTOR NAME] |
| Version / date | 1.0, October 2026 |
| Repository | [GITHUB REPOSITORY URL] |

# 1. Project overview

Goal. Deliver a working, tested and documented chaos-engineering tool that emulates bad network conditions (latency, jitter, burst loss, reordering, duplication, corruption, bandwidth limits) on Linux, with its own impairment engine, a userspace UDP proxy, a kernel tc netem backend, built-in measurement and safety features.

Deliverables. Source code and tests; SRS; Project Plan; Architecture document; UML diagrams (class, sequence, state machine); Progress Report; Roadmap; Git repository with CI; real-VM test evidence; 5-7 minute demonstration at Hour 6.

## 1.1 Success criteria

- All requirements in the SRS (FR-1 to FR-33, NFR-1 to NFR-9) are implemented and each has a verifying test or demo.

- make check is green locally and in GitHub Actions (normal and sanitizer builds).

- sudo scripts/lab.sh demo run on a Linux VM with the output saved as evidence.

- The Hour 6 demo runs in 5-7 minutes without root and without surprises.

## 1.2 Team and roles

| Role | Person | Responsibility |
| --- | --- | --- |
| Developer / architect | [YOUR NAME] | Design, implementation, code review |
| Tester | [YOUR NAME] | Unit, end-to-end, CLI and lab tests; sanitizer runs |
| Documentation / configuration manager | [YOUR NAME] | SRS, plan, reports, Git branching, CI |
| Supervisor | [INSTRUCTOR NAME] | Reviews milestones, confirms syllabus mapping |

# 2. Work breakdown and schedule

Week numbers are relative to the project start. [Adjust the week/date column to your real calendar before submitting.]

| Phase | Main tasks | Output | Planned | Status |
| --- | --- | --- | --- | --- |
| P1 Requirements & research | Study netem, Gilbert-Elliott loss, token bucket, RFC 3550 jitter; decide scope | SRS | Week 1 | Done |
| P2 Design | Module split, profile format shared by all backends, safety design | Architecture, UML | Week 1-2 | Done |
| P3 Core engine + simulator | Profiles/presets/validation, impairment engine, offline sim | profile, impairment, sim + unit tests | Week 2-3 | Done |
| P4 Userspace proxy + probe | poll loop, event heap, per-client sockets, echo/probe metrics, scenarios | proxy, probe + e2e tests | Week 3-4 | Done |
| P5 Kernel backend + lab | tc command generation, safety rails, TTL, signals, veth/netns lab | netem, scripts/lab.sh | Week 4-5 | Implemented; real-VM run to be recorded |
| P6 Review & hardening | Bug-fix review (7 defects), CLI validation, sanitizer runs, CI matrix | CHANGELOG, tests/cli_regress.sh | Week 5 | Done |
| P7 Documentation & configuration management | SRS, plan, architecture, UML, progress report, roadmap; Git repo, branches, tags, push | This document set, GitHub repository | Week 6 | Done (push by student) |
| P8 Real VM test | Run sudo scripts/collect_evidence.sh on a Linux VM; save output | docs/evidence/lab-demo-*.txt | Week 6 | [Student to run] |
| P9 Hour 6 demo | Rehearse scripts/demo_hour6.sh, 5-7 minutes | Live demo | Hour 6 | Script ready; rehearsal pending |

## 2.1 Milestones

| ID | Milestone | Exit criterion |
| --- | --- | --- |
| M1 | Requirements and design approved | SRS + architecture reviewed |
| M2 | Engine verified against theory | 69 unit checks pass |
| M3 | End-to-end path works | probe -> proxy -> echo e2e tests pass (latency, loss, duplication, scenario) |
| M4 | Kernel backend and lab | Command strings tested; lab demo runs on a VM |
| M5 | Quality gate | make check green; sanitizers clean; CI green on GitHub |
| M6 | Submission package | All documents + repository tagged v1.0.0 |
| M7 | Hour 6 demo | 5-7 minute demonstration delivered |

# 3. Configuration management (Git and CI)

## 3.1 Branching model

| Branch | Purpose | Rules |
| --- | --- | --- |
| main | Always releasable; only tagged releases are merged here | Merge from develop with --no-ff; tag every merge |
| develop | Integration branch for finished features | Features merge here via --no-ff |
| feature/* | One branch per piece of work (e.g. feature/docs-requirements-design) | Branch from develop; delete after merge |

## 3.2 Tags

| Tag | Meaning |
| --- | --- |
| v0.1.0 | Baseline: complete, tested code base (engine, simulator, proxy, probe, netem backend, tests, CI) |
| v0.9.0 | Release candidate: documentation and evidence tooling merged into develop |
| v1.0.0 | Submission release on main |

## 3.3 Continuous integration

.github/workflows/ci.yml runs on every push and pull request: it installs g++, make and iproute2, then builds and runs make check (unit, end-to-end and CLI tests) in two modes, normal and sanitizers (-fsanitize=address,undefined). Pushing the repository to GitHub is what starts CI; the green check on the latest commit of main is the evidence.

## 3.4 Commit conventions

Short imperative subject with a type prefix (feat:, fix:, docs:, test:, chore:), one logical change per commit. scripts/git_setup.sh builds exactly the branch and tag structure above.

# 4. Quality plan

| Activity | Tool / command | Pass criterion |
| --- | --- | --- |
| Static checks | g++ -std=c++17 -Wall -Wextra -Wpedantic | Zero warnings |
| Unit tests | make test | 69/69 checks |
| End-to-end tests | make e2e | All assertions pass over real sockets |
| CLI/robustness regression | make cli | All checks pass |
| Sanitizers | make CXXFLAGS="... -fsanitize=address,undefined" check | No ASan/UBSan reports |
| Kernel lab | sudo scripts/collect_evidence.sh | Impaired ping differs from baseline; qdisc removed afterwards |

# 5. Risk management

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | VM kernel has no sch_netem module | Low-Med | High | modprobe sch_netem; lab.sh reports the problem instead of faking success; fall back to dry-run output and userspace proxy for the demo |
| R2 | Impairing the wrong interface locks the user out | Low | High | Lab namespaces, SSH guard, TTL auto-revert, --dry-run |
| R3 | Timing-based tests are flaky on a loaded CI machine | Medium | Low | Wide tolerance bands (e.g. RTT 79-86 ms); re-run; sanitizer build uses -O1 |
| R4 | Syllabus lists device drivers but the project contains none | Medium | Medium | Document the kernel/driver relationship (Architecture section 8); confirm scope with the instructor |
| R5 | Live demo fails (terminals, ports in use) | Medium | Medium | Single-terminal demo_hour6.sh; saved output as backup; --auto mode |
| R6 | Not enough time before submission | Medium | High | Prioritise: evidence run, push to GitHub, fill placeholders |

# 6. Tools and environment

- Language/tooling: C++17, g++, GNU make, bash; Git and GitHub with GitHub Actions.

- Target: Ubuntu Linux VM with iproute2, iputils-ping, ethtool.

- Diagrams: Mermaid (sources in docs/uml/*.mmd) and Graphviz.

# 7. Communication and reporting

Progress is reported in the Progress Report (status, tests, issues, next steps) and tracked in CHANGELOG.md. Questions on scope (for example the device-driver mapping) go to the instructor in writing.